## Sheet1
New Home Construction Checklist
Tap a phase to see the checklist items:
Phase 1: Building Foundations | Column 1
Assessing and Preparing the Soil
Check for problem soils like clay or silt. | FALSE
Ensure the soil is capable of supporting the house. | FALSE
Consult with a building inspector for advice on local soil conditions. | FALSE
If necessary, consult a soils engineer for recommendations. | FALSE
Remove organic matter from the proposed excavation area. | FALSE
Ensure footings rest on undisturbed soil. | FALSE
Use a jumping jack compactor to re-consolidate soil where stumps or rocks were removed. | FALSE
Clean loose material from footing trenches with hand tools. | FALSE
Excavation and Layout
Determine the correct elevation for the bottom of the excavation in advance. | FALSE
Check the bottom of the opening for elevation and levelness as you excavate. | FALSE
For a basement, excavate an opening a few feet wider and longer than the house. | FALSE
For a crawlspace, scrape organic matter but leave the grade. | FALSE
For a monolithic slab, scrape organic matter off the surface. | FALSE
Set up a leveling instrument to establish a level plane. | FALSE
Use offset stakes to preserve the preliminary layout. | FALSE
Record the desired top-of-foundation elevation relative to a benchmark. | FALSE
Mark the excavation area with a line 4 ft. outside the corner stakes. | FALSE
Calculate the exact depth of the excavation based on the top-of-foundation elevation. | FALSE
Footings and Walls
Dig footing trenches to the required depth, below the frost line for your area. | FALSE
Form the footings according to the plan, ensuring the walls will be centered over them. | FALSE
Install rebar as required by local code. | FALSE
Have the footing examined by the building inspector before pouring concrete. | FALSE
Pour the concrete for the footings and form a keyway if specified. | FALSE
After the concrete hardens, lay out the foundation walls on the footings. | FALSE
Check the layout for squareness by measuring the diagonals. | FALSE
Build the foundation walls using poured concrete, concrete blocks, or a permanent wood foundation. | FALSE
For concrete block walls, install rebar and cleanouts in the footings. | FALSE
Grout block cavities as needed. | FALSE
Phase 2: Framing Floors, Walls, and Ceilings
Floors
Measure the foundation to check for squareness and levelness. | FALSE
Snap a chalkline to mark the location of the mudsill. | FALSE
Correct for any low spots on the foundation using shims or patching material. | FALSE
Correct high spots with a grinder or by making adjustments later when installing joists. | FALSE
Attach the mudsills, drilling accurately to fit over anchor bolts. | FALSE
Install a sill seal or caulk to prevent air infiltration. | FALSE
Install girders or basement bearing walls. | FALSE
Sort and crown the joist material before installation. | FALSE
Lay out joist locations on the mudsill, accounting for critical details like stairwells and plumbing. | FALSE
Install rim joists. | FALSE
Install the floor joists, toenailing to the mudsill and nailing to the rim joist. | FALSE
Install the floor sheathing, leaving a small gap for expansion. | FALSE
Follow the specified nailing schedule for the sheathing. | FALSE
Provide for wiring and plumbing by installing blocking. | FALSE
Walls
Lay out the locations of exterior and intersecting walls on the floor. | FALSE
Lay out the details for all exterior wall plates, including rough openings for doors and windows. | FALSE
Fabricate wall components like corners, T-intersections, and headers. | FALSE
Assemble the exterior walls. | FALSE
Sheathe the walls before or after raising them. | FALSE
Raise and brace the exterior walls, ensuring they are plumb and straight. | FALSE
Build and install interior walls. | FALSE
Install the second top plate, overlapping intersecting walls for rigidity. | FALSE
Install blocking and backing for fire protection and to support future installations like cabinets and handrails. | FALSE
Ceilings
Lay out ceiling joist locations on the top plates of the walls. | FALSE
Lay out large openings for stairwells and chimneys. | FALSE
Install joists with the crown up, toenailing to the top plates. | FALSE
Frame a gable-end wall if applicable. | FALSE
Phase 3: Framing Roofs 1: Raftered Roofs
Gable Roof
Find the hypotenuse of the pitch triangle. | FALSE
Determine the dimensions of the measuring triangle to find the height of the ridge and rafter length. | FALSE
Rip the ridge to the correct height and use posts to hold it in place. | FALSE
Install planking across the joists and screw it in place for a work platform. | FALSE
Lay out rafter locations on the ridge. | FALSE
Lay out, cut, and assemble the rafters. | FALSE
Install the rafters, nailing them to the ridge and toenailing to the top plate. | FALSE
Hip Roof
Lay out rafter locations on the walls for king common, hip, and jack rafters. | FALSE
Take key measurements off the top plates. | FALSE
Install ceiling joists and provide backing for drywall where necessary. | FALSE
Cut and install the ridge. | FALSE
Lay out and install the common rafters. | FALSE
Lay out and cut the hip rafters, ripping the material to the correct width and angle. | FALSE
Lay out, cut, and install the jack rafters. | FALSE
Roof with a True Valley
Lay out and install the ridges and common rafters. | FALSE
Prep and install the valley material. | FALSE
Lay out, cut, and install the jack rafters. | FALSE
Doghouse Dormer
Build the opening to the correct size. | FALSE
Frame the walls, cutting plates and studs to match the roof pitch. | FALSE
Cut and install the ridge. | FALSE
Cut and install the common rafters. | FALSE
Lay out and install the valley plate. | FALSE
Lay out and install the valley jack rafters. | FALSE
Phase 4: Framing Roofs 2: Trusses, Eaves, Rakes, and Sheathing
Trusses
Order trusses with a clear understanding of the design loads and roof shape. | FALSE
Store and handle trusses correctly to avoid damage. | FALSE
Set trusses using a crane, telehandler, or by hand. | FALSE
Align trusses using a stringline, laser level, or marks on the bottom chord. | FALSE
Install temporary and permanent bracing as specified in the truss design drawings. | FALSE
Eaves and Rakes
Install subfascia, ripping the top edge to match the roof slope for a full nailing surface. | FALSE
For rake overhangs, build a ladder-type rake or a cantilevered rake. | FALSE
Install the rake boards and rake frieze. | FALSE
For cantilevered rakes, install lookouts and a barge rafter. | FALSE
Sheathing
Install roof sheathing with the long side perpendicular to the rafters/trusses. | FALSE
Leave a 1/8-in. gap between panels for expansion. | FALSE
Follow the specified nailing schedule. | FALSE
Stagger the courses of sheathing. | FALSE
Use H-clips on trussed roofs between panels. | FALSE
Phase 5: Closing the House to the Weather
Roofing the House
Check for the minimum roof pitch required for asphalt shingles. | FALSE
Install an underlayment and drip edge. | FALSE
Lay out the shingle pattern, marking horizontal courses and bond lines. | FALSE
Install the starter course and main courses. | FALSE
Cut shingles to fit around pipes, vents, and other obstacles. | FALSE
Install flashing for all penetrations and junctures. | FALSE
Install ridge and hip caps and vents. | FALSE
Perform a final inspection to clean up dropped nails and seal exposed fasteners. | FALSE
Installing Windows, Exterior Doors, Siding, and Trim
Install a weather-resistive barrier (WRB) on exterior walls, detailing around openings. | FALSE
Flash the bottom, sides, and top of window and door openings. | FALSE
Install windows and exterior doors, ensuring they are plumb and square. | FALSE
Install exterior trim, including corner boards, fascia, and frieze. | FALSE
Seal the end grain of all cut wood or fiber cement siding/trim. | FALSE
Install exterior siding, ensuring all joints allow for movement. | FALSE
Phase 6: Finishing the House – Interior
Wall and Floor Coverings
Order the correct size and quantity of drywall to minimize butt joints. | FALSE
Hang ceilings first, then walls, cutting drywall for all openings and fixtures. | FALSE
Fasten drywall securely and finish all joints and corners with tape and compound. | FALSE
Install solid-sawn tongue-and-groove or plywood paneling if desired. | FALSE
Install wood floors over a layer of tar paper, or install ceramic tile with a proper substrate. | FALSE
Doors
Measure and install prehung doors, ensuring they are plumb, level, and the gaps are consistent. | FALSE
For new doors in existing openings, check the opening and custom-fit the door. | FALSE
Install hardware for all doors. | FALSE
For French, pocket, or bifold doors, follow specific installation and framing instructions. | FALSE
Trim and Cabinets
Install door and window casing, ensuring the jambs are flush with the drywall. | FALSE
Install baseboard, chair rail, and crown molding, using proper joints and cuts. | FALSE
Install backing blocks for crown molding if needed. | FALSE
Check for drawer and appliance clearances before installing cabinets. | FALSE
Install wall cabinets first, followed by base cabinets. | FALSE
Stairs
Build stairs, adhering to code requirements for dimensions and safety. | FALSE
For exterior stairs, use durable materials and protect against frost heave. | FALSE
For interior stairs, account for finished floor thicknesses and a precise fit. | FALSE
Install newel posts, skirtboards, risers, and treads in the correct sequence. | FALSE
Install the balustrade, ensuring balusters are evenly spaced to meet code. | FALSE